## 00_Roadmap
14050526
Phase | Time | Goal | Result
1 | Week 1 | Product definition | Clear specification
2 | Week 2 | Architecture + foundations | Working project skeleton
Week 3
Week 4
3 | Month 2 | Authentication + users | Accounts/profiles
4 | Month 3 | Experiences | First real posts
5 | Month 4 | Social networking | Follow/like/comment
6 | Month 5 | Map platform | Full spatial experience
7 | Month 6 | Places + Discovery | Place-centric platform
8 | Month 7 | Personal/collective maps | Emotional & memory maps
9 | Month 8 | Polish + security | Beta-ready
10 | Month 9 | Launch + feedback | Real users
11 | Month 10 | Monetization | First business model
Month 11
Month 12

## 01_Product Definition
MVP |  |  |  |  | future features
Users | Experiences | Social | Map | Places | AI | Tourism | Business Accounts | Analytics | Emotional Heatmaps | Life Maps | Memory Trails | Monetization | APIs
Register | Create experience | Like | Display experiences | Place page
Login | Select location | Comment | Click experience | Experiences associated with place
Profile | Story | Share | Filter by emotion
Follow/Unfollow | Emotion |  | Search location
Date
Photo
Visibility

## 02.0_Architecture
Data Model
Frontend | Backend | Database
HTML | Python | PostgreSQL
CSS | FastAPI | PostGIS
JavaScript |  |  | Database Structure
OpenLayers |  |  | users | experiences | locations | places
|  |  | followers | geometry | X | geometry
|  |  | comments | emotion | Y | name
|  |  | likes | story |  | category
|  |  | experiences | date |  | experiences
media
place

## 02.1_Foundation
application should have: | these should be running:
Frontend | Frontend running
REST API | Backend running
FastAPI | Database connected
PostgreSQL/PostGIS | API responding
PostGIS enabled
Git repository
Environment variables
Development/production configuration

## 03_Authentication + users
features to be built
Registration | Login | Logout | Profile | Follow system
email |  |  | profile picture
username |  |  | username
password |  |  | bio
followers
following
experience count

## 04_Experiences
Create an Experience
Location Selection | Written Content | Emotion | Media | Visibility | Publish | is anonymous
Select location | Title | Happiness | Upload photo | Public | Publish experience | identified
| Story | Nostalgia | Upload video | Followers |  | anonymous
| Date | Peace |  | Private
|  | Sadness |  | Anonymous
Fear

## 05_Social Networking
Network System
Likes | Comments | Sharing | Following | Feed | Experiences:
different emojies |  |  |  | not chronological | from people you follow
near you
interesting places
Milestone:
[6 empty] | 1 | Follow
[6 empty] | 2 | Post
[6 empty] | 3 | Like
[6 empty] | 4 | Comment
[6 empty] | 5 | Share

## 06_Map platform
Map platform
| Experience Map | Emotion filters
| Use OpenLayers | Love
| Use clustering | Happiness
| Use vector layers | Nostalgia
| Use spatial queries | Peace
| Use popup cards | Sadness
Fear
Anger
etc.
result | Every public experience appears on the map. | the map shows experiences associated with filtered emotions

## 07_Places + Discovery
Instead of thinking: A post has coordinates. Think: A place has experiences. for each specific place page
Central Park
Recent memories | Popular experiences | Most common emotions | Photos | Map | People who experienced this place

## 08_Personal-collective maps
Personal-collective maps
Personal Life Map | Memory Timeline | Emotional Map | Memory Trails

## 09_Privacy-Security
Privacy | Security
Public | Password hashing
Followers | JWT/session security
Private | Input validation
Approximate location | Rate limiting
File validation
Authorization checks

## 10_Launch + feedback
Launch to: 20–50 people from friends
ask them to:
Create an account
Add 5 memories
Explore the map
Follow someone
Comment
Find a place
Create a memory trail

## 11_Monetization
Monetization experiments
Business profiles
Featured places
Premium users
Business analytics
Spatial Intelligence