## Sheet1
Week 1 | Week 2 | Week 3 | Week 4
Create GitHub repository | Connect FastAPI → PostgreSQL | Registration | Create experience
Define MVP | Create users table | Login | Select location on OpenLayers
Design database | Create experiences table | Authentication | Save geometry in PostGIS
Create project structure | Create places table | Profile | Save story
Install PostgreSQL/PostGIS | Create initial API | Follow/unfollow | Save emotion
Create initial FastAPI project | Connect React → API |  | Display experience on map
Create React project
result:
Register
Login
Open map
Click a location
Write a memory
Select an emotion
Publish
See your memory on the map.